## Slide 1
INTOSAI WORKING GROUP ON KEY NATIONAL INDICATORS
Dmitry Zaytsev
Accounts Chamber of the Russian Federation
Sofia, March 25, 2015
VIII MEETING
WORKING GROUP PLAN FOR 2015

## Slide 2
WORKING GROUP PLAN FOR 2015
№ | Activities | Time | Coordinator
1. | The 8th meeting of the WG | March 25-26, 2015 Sofia (Bulgaria) | SAI of Bulgaria, Secretariat, WG members
2. | Further work concerning the initiative to research countries preparedness to use the KNI systems in SAI activities |  | 
2.1 | The WG member-states providing information for the Questionnaire concerning the countries preparedness to use the KNI systems in SAI activities | April, 2015 | WG members
2.2. | Finalizing the work on the Questionnaire concerning the countries preparedness to use the KNI systems in SAI activities | May 25, 2015 | Secretariat

## Slide 3
WORKING GROUP PLAN FOR 2015
№ | Activities | Time | Coordinator
3. | Guidance Document for the KNI use in SAIs activities on the base of the White Paper |  | 
3.1 | Preparing the draft of the Guidance Document for the KNI use in SAIs activities | July 1, 2015 | Secretariat
3.2. | Agreeing the draft of the Guidance Document for the KNI use in SAIs activities by WG member-states | September 1, 2015 | WG members Secretariat,
3.3 | Preparing the final version of the draft of the Guidance Document for the KNI use in SAIs activities | October 1, 2015 | Secretariat

## Slide 4
WORKING GROUP PLAN FOR 2015
№ | Activities | Time | Coordinator
4. | 7th KSC Steering Committee Meeting October 15-16, 2015 Washington D.C., USA |  | 
4.1 | Preparing the report on the Working Group activities 2014-2015 and agreeing it by WG members | October , 2015 | Secretariat WG members
4.2. | Presentation of the draft of the Guidance Document for the KNI use in SAIs activities | October 15-16, 2015 | Secretariat

## Slide 5
WORKING GROUP PLAN FOR 2015
№ | Activities | Time | Coordinator
5. | 67th INTOSAI Governing Board Meeting, November 10-11, 2015, Abu-Dhabi, United Arab Emirates |  | 
5.1 | Preparing the report on the Working Group activities 2014-2015 and agreeing it by WG members | October, 2015 | Secretariat, WG members
6. | Considering a possibility to organize training for SAI self-assessment and use of KNIs in their activity | 2015-2016 | Secretariat, WG members

## Slide 6
WORKING GROUP PLAN FOR 2015
№ | Activities | Time | Coordinator
7. | New version of the KNI Knowledge Base |  | 
7.1. | WG member-states designating contact persons responsible for communication on the KB issues and providing the Secretariat with this information | April 7, 2015 | WG members
7.2. | Publishing the new version of the Knowledge Base on the website of the Accounts Chamber of the Russian Federation | April 13, 2015 | Secretariat
7.3. | WG member-states providing suggestions on the new version of the Knowledge Base. Collecting and reviewing the feedback received | April, 2015 | WG members, Secretariat

## Slide 7
WORKING GROUP PLAN FOR 2015
№ | Activities | Time | Coordinator
7.4. | WG member-states designated persons providing initial information (files, links, documents) to be included in the new version of the Knowledge Base | May – June, 2015 | WG members
7.5. | Placing the initial information in the new version of the Knowledge Base and having it verified by WG member-states designated persons | July-August, 2015 | WG members, Secretariat
7.6. | WG member-states designated persons providing further information related to the new version of the Knowledge Base | Entire period | WG members

## Slide 8
WORKING GROUP PLAN FOR 2015
№ | Activities | Time | Coordinator
8. | New framework agreement between INTOSAI and OECD |  | 
8.1. | Informing the INTOSAI General Secretariat on the meeting between the WG Secretariat and OECD in 2014, Proposing the INTOSAI General Secretariat to sign a new framework agreement between INTOSAI and OECD | April 2015 | Secretariat
8.2. | Preparing a draft framework agreement between INTOSAI and OECD and agreeing it with the WG member-states | June 1, 2015 | Secretariat, WG members

## Slide 9
WORKING GROUP PLAN FOR 2015
№ | Activities | Time | Coordinator
8.3. | Sending a draft framework agreement between INTOSAI and OECD to the INTOSAI General Secretariat for the adoption | June, 2015 | Secretariat
8.4. | Agreeing a draft framework agreement between INTOSAI and OECD and agreeing it with the OECD | July 1, 2015 | Secretariat

## Slide 10
WORKING GROUP PLAN FOR 2015
№ | Activities | Time | Coordinator
9. | Monitoring the international initiatives in the sphere of the socio-economic development taking into account recent investigations in this sphere | Entire period | Secretariat, WG members
10. | Developing contacts with the WB, the WEF and other organizations | Entire period | Secretariat, WG members
11. | Developing cooperation with INTOSAI Working Groups and regional economic organizations | Entire period | Secretariat, WG members

## Slide 11
WORKING GROUP PLAN FOR 2015
№ | Activities | Time | Coordinator
12. | Maintaining INTOSAI Working Group on KNI website | Entire period | Secretariat, WG members
13. | Preparing the 9th meeting of the Working Group | Entire period | SAI of Armenia, Secretariat, WG members

## Slide 12
VIII MEETING
THANK YOU!
INTOSAI WORKING GROUP ON KEY NATIONAL INDICATORS